## Slide 1
www.uneekprojects.com
Notes: <number>

## Slide 2
EVENT MANAGEMENT
Notes: <number>

## Slide 3
EVENT MANAGEMENT
Planning, Coordinating & Management of a Successful Event
Ten Steps for Success!
Notes: <number>

## Slide 4
EVENT MANAGEMENT
Pick/Identify Event
Establish event goals and objectives
Identify event timeline
Determine location/venue
Create marketing plan and promotion strategies
Notes: <number>

## Slide 5
EVENT MANAGEMENT
6) Staffing / Assign team roles
7) Sales & marketing process
8) Event planning & logistics
9) Day of Event / Event Mgmt
10) Have Fun!
Notes: <number>

## Slide 6
Select / Identify Event
3 v 3 Street Soccer Tourney
Notes: <number>

## Slide 7
Event Goals / Objectives
Generate Revenue / Turn Profit (minimize expenses)
Offer event that appeals to participants, spectators and sponsors
Create exciting event (brand) with long term roots in community
Notes: <number>

## Slide 8
Event Timeline
Allow at least 90 days in advance to manage, plan and organize a successful event…
Notes: <number>

## Slide 9
Determine location/venue
Consider your options
How many spectators?
Traffic flow?
Sponsor appeal?
Vendor locations?
Parking?
Notes: <number>

## Slide 10
Create marketing plan and promotion strategies
Review goals
Identify target audience
BRAND development
Collateral materials
Sales, marketing & promotional planning
Notes: <number>

## Slide 11
Staffing / Assign Team Roles
Identify all areas needing help
Evaluate staff, team and volunteer strengths
Assign roles accordingly
Notes: <number>

## Slide 12
Sales & Marketing Process
Pre-registration
Sponsorship
Vendors
Promote event to public (spectators)
Merchandising
Notes: <number>

## Slide 13
Event Planning & Logistics
Risk management
Permits
Security
Reserving space
Restrooms
Parking
Concession locations etc
Notes: <number>

## Slide 14
Day of Event / Event Management
Event day checklist
Pre-game/event “run through”
Communication is key!
Emergency response plan
Notes: <number>

## Slide 15
HAVE FUN!
Notes: <number>

## Slide 16
www.uneekprojects.com
Notes: <number>